## MGL Farmers Daily Report
date | time | Enter Your ID Acronym | Select Your Section | Select Your Team | Tasks (AM) | Tasks (PM) | Incidence/Delay | Comments | _id | _uuid | _submission_time | _validation_status | _notes | _status | _submitted_by | __version__ | _tags | _index
2023/03/15 | 18:07:55 | JOTI | Vegetable | Team 1 | Laying of mulching films on the open field and partial filling of sand along the edges of the mulching films. | Proper filling of soil along mulching films edges. | Late arrival of mulching films to the farm. | Cool weather at first but later Scorching which require request of drinking water by trainees. | 225342892 | dfc31411-d2ac-44d2-a7be-3f53d35f86fa | 2023-03-15 17:10 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 1
2023/03/15 | 19:01:29 | OYOY | Vegetable | Team 2 | Laying of mulching film on the open field | Filling of mulching film with sand | Late arrival of mulching film | Nil | 225354685 | 8a322eed-d636-4ff3-b33d-456c9c3bae27 | 2023-03-15 18:05 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 2
2023/03/16 | 15:22:19 | ADAD | Cocoa | Team 1 | Spraying of Cocoa farm | Spraying of Cocoa farm | Nil | Work is moving fine | 225601466 | d499b16e-a560-40fd-9144-2092789296c7 | 2023-03-16 15:07 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 3
2023/03/16 | 16:00:23 | DELU | Cocoa | Team 1 | Spraying of insecticide | Con't. of spraying of insecticide | Nil | The weather was so favourably | 225601630 | b445e177-1066-4a03-a561-9024a2bd919b | 2023-03-16 15:07 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 4
2023/03/16 | 17:28:47 | OYOY | Vegetable | Team 2 | Laying of mulching film | Irrigation of green house and open field | Fuel delay | Nil | 225646364 | 222e5675-a0dd-4063-ad39-8edb7c4d3cc0 | 2023-03-16 18:07 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 5
2023/03/15 | 16:16:34 | EZAZ | Vegetable | Team 3 | Laying of mulching film . | continuity of laying mulching film and putting sand. | delay of supplying of mulching film at d farm. | No comments | 225654139 | e4d24bf6-8c9b-4ecd-876a-736c76c9782b | 2023-03-16 18:50 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 6
2023/03/16 | 19:44:40 | EZAZ | Vegetable | Team 3 | Laying of mulching film. | continuity of laying mulching film and putting of sand | non | there where not enough of man power in the farm and it was too stressful. | 225654142 | 3e88b929-08b4-405c-ac75-430d4ec2de17 | 2023-03-16 18:50 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 7
2023/03/16 | 21:25:33 | JOTI | Vegetable | Team 1 | Laying of mulching films on open field. | Laying of mulching films and filling of soil along the sides of the mulching films. | Nill. | Nill. | 225668960 | 3a35dda5-9f97-4f79-b740-0061107acd69 | 2023-03-16 20:28 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 8
2023/03/17 | 16:05:28 | RODA1 | Cocoa | Team 4 | Spraying | Spraying | Fuel and water delayed | Fumigation continues and the Camerunians are doing their job | 225868160 | e1bd2812-4425-4a04-bea6-08db4c595453 | 2023-03-17 15:08 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 9
2023/03/17 | 16:48:44 | DELU | Cocoa | Team 1 | Con't of fumigation of cocoa and other works like clearing | Fumigation and other works continue | There's no enough water to use today | There should be availability of water to avoid delay | 225879431 | fce71f16-3d21-41ab-882c-2c351e33ec17 | 2023-03-17 15:52 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 10
2023/03/17 | 16:51:07 | ADAD | Cocoa | Team 1 | Spraying of Cocoa | Spraying of Cocoa plantation | We have delay in the morning with water | Water is very important to our | 225881162 | a3c28770-5233-45af-9c4d-c446393687c3 | 2023-03-17 15:58 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 11
2023/03/17 | 16:02:17 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field | Continuation of irrigation of green house and open field | Late arrival of petrol | Nil | 225905982 | bb54d5ec-d6a2-4e91-8ef5-bc1f350542b7 | 2023-03-17 17:48 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 12
2023/03/16 | 15:56:28 | LASU | Cocoa | Team 1 | Spraying the Cocoa trees | Spraying the Cocoa trees | Nil | Smooth job done | 225912101 | b564ae48-821c-4578-b3a4-105bbc254b33 | 2023-03-17 18:19 |  |  | submitted_via_web | lasu_mgl | vEyhG35agJ8ci5haXwXtix |  | 13
2023/03/17 | 19:14:22 | LASU | Cocoa | Team 1 | Fumigation/praying continue in Cocoa farm while others also continue with the bush clearing... | Same as morning report... | Fuel/water delayed our work in the morning.... | We have a great day | 225912115 | 07b0d325-6fbe-4ae3-9b4f-41dc3eb5791d | 2023-03-17 18:19 |  |  | submitted_via_web | lasu_mgl | vEyhG35agJ8ci5haXwXtix |  | 14
2023/03/17 | 19:51:26 | JOTI | Vegetable | Team 1 | Laying of mulching films on open field and partial filling of the ridges. | Laying of mulching films (Contd). | Low manpower to reach task for the day. | Human strength deterioration | 225920105 | 6c1824f5-ceef-4a81-94af-9365ac05983e | 2023-03-17 18:57 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 15
2023/03/17 | 20:15:27 | EZAZ | Vegetable | Team 3 | Laying of mulching films at the open field and putting of sand. | continuity of laying of mulching films and putting of sand | Low man power so it slows d work | every day by day man power is reducing and it's so stressful to me and now the veins at arms are over stressed so its now paining me. pls do something about it thanks. | 225923171 | bb498f18-cfdb-4fa7-82b7-3d6e5caa47f7 | 2023-03-17 19:21 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 16
2023/03/18 | 18:45:37 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field | Irrigation of green house and open field | None | None | 226117432 | c70560f1-11a4-49c0-b6a1-4757b35501b2 | 2023-03-18 17:49 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 17
2023/03/18 | 20:35:32 | EZAZ | Vegetable | Team 3 | Laying of mulching films and putting of sand. |  |  |  | 226131950 | 8c901fb9-32bf-4bad-bbf0-64379c7487bb | 2023-03-18 19:45 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 18
2023/03/18 | 23:06:32 | JOTI | Vegetable | Team 1 | Laying of mulching films. Filling of soil along the edges of the mulching films. | Nill | Low manpower affecting target. | Nill. | 226143305 | af448a93-2e3e-49f3-8494-1e8920243783 | 2023-03-18 22:08 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 19
2023/03/20 | 16:03:10 | LASU | Cocoa | Team 1 | Spraying continue in Cocoa farming while the malams continue the bush clearing.... | Same as morning work | Nil | Good weather.... | 226478175 | 6fa835b2-5586-4b4c-8ead-e8bd192d4fa8 | 2023-03-20 15:07 |  |  | submitted_via_web | lasu_mgl | vEyhG35agJ8ci5haXwXtix |  | 20
2023/03/20 | 10:37:29 | RODA | Cocoa | Team 1 | Spraying on Cocoa farm | Cont, spraying on Cocoa farm | Nil | Good weather | 226478769 | 424c5347-faf0-49b5-941d-031bcd3de032 | 2023-03-20 15:10 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 21
2023/03/20 | 16:10:39 | DELU | Cocoa | Team 1 | Funmigation/Spraying on cocoa fsrm using Cyprus insecticide | Con't of fumigation on cocoa farm | Nil | Good weather | 226478988 | 6ef9d1b2-3006-4493-83f2-6aded931201a | 2023-03-20 15:12 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 22
2023/03/20 | 18:15:38 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field | Irrigation of green house and open field | Nil | The rain that fell helps the open field | 226507543 | 825f3600-ccd2-4f70-873f-1603c52a8a9d | 2023-03-20 17:16 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 23
2023/03/20 | 21:19:18 | JOTI | Vegetable | Team 1 | Filling of soil along the edges of the mulching films. | Laying of mulching films. | Nill. | Nill. | 226541897 | 655923ca-6c06-487d-a80f-9adb2851dd1b | 2023-03-20 20:22 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 24
2023/03/21 | 17:45:04 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field. Raising of nursery ( Super habanero and platinum) | Irrigation of green house and open field | Nil | Nil | 226764700 | a5dd30c1-c9b7-4e79-8fcc-128f7dbbee66 | 2023-03-21 16:47 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 25
2023/03/21 | 19:02:03 | JOTI | Vegetable | Team 1 | Filling of soil on mulching films | Filling of soil on mulching films | Drilling machine component not working with completely, already taken out for welding | Nill. | 226781818 | fe11ff7f-6f7f-4cfc-98e5-e3c36f504b37 | 2023-03-21 18:05 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 26
2023/03/20 | 20:24:31 | EZAZ | Vegetable | Team 3 | Putting of sand on the mulching film. | laying mulching film and putting of sand. |  |  | 226800263 | 94a20c5c-0e4c-49a8-a37a-817f6d85a9f4 | 2023-03-21 20:01 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 27
2023/03/21 | 20:57:19 | EZAZ | Vegetable | Team 3 | filling of sand on the mulching film | Laying of mulching film and putting of sand. | broken drilling iron so we couldn't commence on drilling of holes fr staking . |  | 226800265 | 13135510-4fc8-47bc-a818-59bf7e3c0a30 | 2023-03-21 20:01 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 28
2023/03/22 | 06:48:45 | DELU | Cocoa | Team 1 | Funmigation/Spraying of Insecticide on cocoa farm | Con't of funmigation on the cocoa farm | Nil | Good weather and there is enough water to use today | 226862705 | edd92639-848d-4c05-90e0-b6ec7af584a2 | 2023-03-22 05:50 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 29
2023/03/21 | 17:01:40 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is going on good, but we need Milo and milk to take for more energy to carry on with the task. | 226950410 | 97daa950-a8b0-45b0-9559-06563336b465 | 2023-03-22 11:38 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 30
2023/03/20 | 17:09:43 | ADAD | Cocoa | Team 1 | Spraying of Cocoa in the farm | Spraying of Cocoa in the farm | Nil | Spraying is going on very well, but we need milk and Milo for energy. Because the work is really hard. | 226950483 | ee6693e9-3dc7-4f51-a485-f7c1f3e86840 | 2023-03-22 11:39 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 31
2023/03/22 | 09:45:52 | DELU | Cocoa | Team 1 | Funmigation/Spraying on cocoa farm using cyrups insecticide | Con't on spraying/funmigation on cocoa farm | Nil | DELU | 227036971 | efbe1d55-0327-47b8-b190-5e57f3ca2c53 | 2023-03-22 16:29 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 32
2023/03/22 | 18:45:32 | LASU | Cocoa | Team 1 | Works continue in Cocoa farm... Spraying and bush clearing... | Same as morning work | Nil | Cool weather | 227056200 | 83c399b1-e1d8-4854-b3fe-b323b7e6e0e4 | 2023-03-22 17:48 |  |  | submitted_via_web | lasu_mgl | vEyhG35agJ8ci5haXwXtix |  | 33
2023/03/22 | 18:13:15 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field | Irrigation of green house and open field | Nil | Due to rain fall helps the open field | 227073711 | 4a55fa5c-664f-4b67-a266-9dca1a1f9bf9 | 2023-03-22 19:22 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 34
2023/03/22 | 20:49:27 | JOTI | Vegetable | Team 1 | Laying of mulching films. Digging of holes and insertion of bamboos on the ridges. | Digging of holes and insertion of bamboos on the ridges. | Delay in arrival of drilling component that was taken to the welder. | Trainees fairly available for field work as they were engaged on other activities outside open-field | 227078923 | 2d3be21f-08f3-4e22-ad28-c70391d8e6f5 | 2023-03-22 19:54 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 35
2023/03/22 | 16:26:06 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is going fine. | 227100574 | 0f7853f7-3fe8-44e6-bfea-d3fa29a9cbc7 | 2023-03-22 22:38 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 36
2023/03/22 | 09:48:11 | RODA | Cocoa | Team 1 | Spraying | Spraying | Not at all | Good weather | 227306501 | f3f6a3b2-ff11-4f30-b76e-a241d27add9a | 2023-03-23 15:56 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 37
2023/03/23 | 16:53:25 | RODA | Cocoa | Team 1 | Spraying | Spraying | Nil | Good weather | 227306503 | 814ba243-00d3-44f0-aa05-06f59f73cd96 | 2023-03-23 15:56 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 38
2023/03/23 | 16:53:30 | DELU | Cocoa | Team 1 | Fumigation/spraying of insecticide on cocoa farm | Con't of fumigation/spraying in cocoa farm | Nil | No delay | 227306718 | f44ea857-cb1f-4ba1-9cd3-53b5511a587c | 2023-03-23 15:57 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 39
2023/03/23 | 16:53:02 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is going on fine | 227308615 | fd5cc01f-1fa6-40f8-a518-de320d27cff0 | 2023-03-23 16:05 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 40
2023/03/23 | 17:49:30 | EZAZ | Vegetable | Team 3 | drilling of holes and staking of bamboos. | Drilling of holes. Laying of mulching films and putting of sands. | Fuel for the drilling machine | please man power needed | 227320164 | ab8c8e3f-39cd-406e-845e-bb6347577366 | 2023-03-23 16:55 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 41
2023/03/23 | 20:12:44 | JOTI | Vegetable | Team 1 | Drilling of bamboo holes and insertion of bamboos on the ridges. | Drilling of bamboo holes. Laying of mulching films on the ridges. | Fuel for driller. | Not as fast as projected because we're operating with just one driller | 227348142 | 72ba565e-e9b0-43da-946a-ea3001693606 | 2023-03-23 19:16 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 42
2023/03/24 | 08:13:04 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field | Irrigation of green house and open field | Late arrival of fuel | Nil | 227427028 | b0ca848f-230c-4b97-a161-23501bf427c9 | 2023-03-24 07:14 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 43
2023/03/24 | 18:49:01 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Yes I have delay with my spring machine today, I have inform MR. OLA about it | Please I need to fix my spring machine | 227584924 | 85355443-f497-4171-9951-8db6174be387 | 2023-03-24 17:54 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 44
2023/03/24 | 20:20:35 | RODA | Cocoa | Team 1 | Spraying | Spraying | Lack of fuel, one of the machine broke down and was trying to be fixed | We went to another location of Cocoa farm and try to commence the task, but unable bcos of fuel and some other delay encountered in the process | 227598988 | c521941e-8f3d-40cd-b3ff-5dac16f7992a | 2023-03-24 19:32 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 45
2023/03/24 | 21:03:30 | JOTI | Vegetable | Team 1 | Drilling of bamboo holes. Staking of bamboo rods. Laying of mulching films. | Staking of bamboo rods. | Malfunctioning of drilling engine which later stopped working even after several attempt to make it work. The work continued with the use of cutlass but reduced in speed and accuracy of the perfect result expected. | Nill. | 227603419 | 1f43e882-1e1a-4d86-b64d-f92d9ce9435e | 2023-03-24 20:08 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 46
2023/03/24 | 20:36:23 | EZAZ | Vegetable | Team 3 | Drilling of holes fr staking and staking of bamboos | Staking of bamboos and Laying of mulching films. | Unable to proceed of drilling of holes due to malfunction of drilling machine. | please we need more man power | 227757993 | f51c1f4f-7f04-410d-b468-73239fa4c425 | 2023-03-25 17:11 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 47
2023/03/25 | 18:03:18 | EZAZ | Vegetable | Team 3 | Staking of bamboos |  | malfunction of drilling machine | pls we need more man power | 227758003 | b2207402-9724-4aa3-b451-a401923a6ef4 | 2023-03-25 17:11 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 48
2023/03/25 | 19:57:53 | OYOY | Vegetable | Team 2 | Irrigation of green house. Applying of calcium nitrate | Irrigation of green house. | Nil | Continuous rain fall helps the open field | 227773279 | 36cc1b04-3653-4cea-98fb-05d452a11535 | 2023-03-25 18:58 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 49
2023/03/25 | 20:39:23 | JOTI | Vegetable | Team 1 | Staking of bamboo on the ridges. | Nill. | Driller faulty thereby the use of cutlass for digging was adopted but was slow. | Nill. | 227777805 | 461e62a7-c7ec-4dbb-828b-b0511b320706 | 2023-03-25 19:43 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 50
2023/03/25 | 21:10:49 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation | Spraying of Cocoa plantation | Nil |  | 227780152 | 9796bc29-508e-4b1b-b699-eb7c0d144cc2 | 2023-03-25 20:12 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 51
2023/03/27 | 10:18:04 | RODA | Cocoa | Team 1 | Spraying | Spraying | No delay | Smooth weather. Mission accomplished | 228120974 | be141133-3b68-474e-8ee6-01e66c2e3861 | 2023-03-27 15:17 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 52
2023/03/27 | 16:14:17 | DELU | Cocoa | Team 1 | Fumigation/Spraying on cocoa farm using Insecticide | Con't on fumigation/spraying on cocoa farm | Nil | Availability of water and good weather | 228121264 | 5f125825-b98f-446c-b723-9445b9e9f48e | 2023-03-27 15:19 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 53
2023/03/22 | 10:09:41 | LASU | Cocoa | Team 1 | Works in progress in Cocoa farm... Clearing and spraying | Same as morning work | Nil | Cool weather | 228151340 | 1dca6397-40ee-439b-8b02-7ee9d7506074 | 2023-03-27 17:33 |  |  | submitted_via_web | lasu_mgl | vEyhG35agJ8ci5haXwXtix |  | 54
2023/03/27 | 21:16:58 | JOTI | Vegetable | Team 1 | Drilling of bamboo holes on ridges. Erecting of bamboo rods. Opening of holes on mulching films . | Drilling of bamboo holes on ridges. Erecting of bamboo rods. Opening of holes on mulching films | Nill | Nill | 228176231 | 657b7cc5-f52b-49e1-8b3c-da862d2b280e | 2023-03-27 20:19 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 55
2023/03/28 | 18:35:39 | OYOY | Vegetable | Team 2 | Irrigation of green house. Application of AGROVERT(11 46 14) on okra | Irrigation of green house | Late arrival of fuel | Nil | 228431554 | e77d5c82-eaad-490a-843c-37cc1c2ecff9 | 2023-03-28 17:38 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 56
2023/03/29 | 18:12:07 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field. Application of fungicide (SAFF) | Irrigation of green house and open field. Application of fertilizer (AGROVERT 11 46 14) | Nil | Nil | 228709538 | acea61b0-428f-48e5-a270-56d59504736a | 2023-03-29 17:13 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 57
2023/03/29 | 20:05:38 | JOTI | Vegetable | Team 1 | Drilling of holes for bamboo staking. Making of holes for transplanting. | Drilling of holes for bamboo staking. Making of holes for transplanting. | Nill. | Constant use of drilling machine (Earth Auger) affects body system causing sleepless nights. | 228735618 | af4955af-d753-4603-8dca-df6fcfa8c4a3 | 2023-03-29 19:11 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 58
2023/03/27 | 20:36:04 | EZAZ | Vegetable | Team 3 | Drilling of Holes and staking of bamboos. Making of holes fr planting . | Drilling of holes and staking of bamboos. Making holes fr planting . |  |  | 228736260 | f2b3b398-7f4e-43d9-bfb1-5c49d68beb9f | 2023-03-29 19:14 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 59
2023/03/29 | 20:04:15 | EZAZ | Vegetable | Team 3 | Drilling of holes and staking of bamboos. Making holes fr transplanting . | Drilling of holes and staking of bamboos. Making holes for transplanting. |  | working on fire to make holes affect me, milk needed pls . | 228736265 | c8dd40dc-a221-4d94-a1bf-6300b7d29656 | 2023-03-29 19:14 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 60
2023/03/27 | 21:28:01 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 228953479 | ec854ff7-62b5-404c-8d79-d40c16b80333 | 2023-03-30 14:37 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 61
2023/03/29 | 18:24:22 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation | Spraying of Cocoa plantation | Nil | Work is moving | 228953502 | 02d86538-1763-4405-822d-dff65eb7fb01 | 2023-03-30 14:37 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 62
2023/03/30 | 15:37:29 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving on | 228954654 | 5df050c4-81d8-418c-8415-2519e012aaab | 2023-03-30 14:41 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 63
2023/03/30 | 09:31:30 | DELU | Cocoa | Team 1 | Fumigation/Spraying on cocoa farm using Insecticide and foliar cocoa | Con't on fumigation and Spraying using application of foliar cocoa and insecticide | Nil | No delay | 228965222 | 9397e28e-80bb-495d-8fb6-2b126f5d7fa7 | 2023-03-30 15:12 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 64
2023/03/30 | 16:11:50 | RODA | Cocoa | Team 1 | Spraying | Spraying | Nill | Good weather and was able to meet the target | 228965964 | 1ed68c46-c8fd-4c3e-9f3b-1ac0edd489b3 | 2023-03-30 15:14 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 65
2023/03/30 | 19:15:27 | OYOY | Vegetable | Team 2 | Irrigation of green house. Application of fertilizer in the open field (AGROVERT 11 46 14) | Irrigation of green house | Nil | Rain fall helps the open field | 229012221 | e7a63783-871d-4707-bb8e-a411be41bb92 | 2023-03-30 18:16 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 66
2023/03/30 | 22:07:02 | EZAZ | Vegetable | Team 3 | Drilling of holes and staking of bamboos. Punching of holes for making of holes for transplanting . | Drilling of holes and staking of bamboos. Making holes fr transplanting. | wet woods because of rain, so we couldn't set fire to make holes for transplanting in the morning, and rain in the evening also quench the fire, so we couldn't continue . |  | 229043090 | 74e2f6d3-e837-49a8-8304-40dd5986af04 | 2023-03-30 21:25 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 67
2023/03/31 | 17:42:14 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Yes I have delay with my spraying machine is not working fine again, it slow down my work in the farm today. Please we need to fix the machine on time for the work to move fast. | Please I want my spraying machine to work. | 229255679 | ce002254-c869-4374-8533-e8a7dbd8add1 | 2023-03-31 16:49 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 68
2023/03/31 | 20:28:37 | JOTI | Vegetable | Team 1 | Drilling of holes for bamboo staking. Erecting of bamboo on the ridges. | Erecting of bamboo on the ridges. Transfer of binding wires from the then tatse open-field to the new open field. | Nill. | Nill. | 229286638 | 28d51cb1-d720-4d3b-b84d-9a6b83fd11c6 | 2023-03-31 19:30 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 69
2023/03/31 | 19:43:02 | OYOY | Vegetable | Team 2 | Irrigation of green house.Application of Halakat( insecticide) | Irrigation of green house and open field | Nil | Nil | 229287427 | f7e03c3d-2370-4ff7-b04b-6a37b26024c8 | 2023-03-31 19:35 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 70
2023/04/01 | 17:36:51 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | My spraying machine is not yet fix | Work is moving | 229449343 | bb01eedf-779a-46ba-867f-c30c1a4f5f8b | 2023-04-01 16:52 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 71
2023/04/01 | 18:58:57 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field. Staking of green house | Irrigation of green house | Nil | Nil | 229459935 | 20464b76-06d7-4074-9bd0-a5e78cae91da | 2023-04-01 18:00 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 72
2023/03/31 | 22:42:57 | EZAZ | Vegetable | Team 3 | Drilling of holes and staking of bamboos. making punch on the mulching film for making of holes fr transplanting. | Drilling of holes and staking of bamboos. | wet woods it disrupt us from making holes for transplanting . |  | 229461296 | 4cf60fd1-c1f9-4119-af90-70eb40f57469 | 2023-04-01 18:13 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 73
2023/04/01 | 19:11:11 | EZAZ | Vegetable | Team 3 | Tying binding wire on the bamboos and making of holes fr transplanting |  |  |  | 229461297 | 2dbd7018-f0dc-415a-b8e8-ff22d4a7f811 | 2023-04-01 18:13 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 74
2023/04/01 | 20:48:04 | JOTI | Vegetable | Team 1 | Drilling of bamboo holes. Making of holes for transplanting. Tying of binding wire on bamboos and about 17beds completed. | Nil. | Nill. | Nill. | 229470626 | b1c2a585-1206-4474-8e0d-790e4d78088c | 2023-04-01 19:50 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 75
2023/04/03 | 20:06:36 | JOTI | Vegetable | Team 1 | Fixing of binding wire on bamboos for staking. Making holes on mulching films for transplant. | Fixing of binding wire on bamboos for staking. Making holes on mulching films for transplant. | Nill. | Nill. | 229841671 | 89923bab-eb87-4155-97a7-9a46776c0621 | 2023-04-03 19:09 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 76
2023/04/03 | 17:11:31 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field. | Irrigation of green house. Spraying of Golan(insecticide) | Late arrival of fuel | Nil | 229851886 | 92f6a3f6-bbea-4f32-b64a-2eb26f946519 | 2023-04-03 20:42 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 77
2023/04/04 | 08:04:40 | DELU | Cocoa | Team 1 | Fumigation/Spraying on cocoa farm phase 3 using Insecticide with cocoa foliar | Fumigation/Spraying on cocoa farm phase 3 using Insecticide with cocoa foliar | Nill | Readilywater and good weather condition | 230015437 | 0d1653f5-7dc7-45d9-9f47-849ae40b0ba2 | 2023-04-04 14:22 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 78
2023/04/04 | 19:15:57 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field. | Irrigation of green house and open field. Application of fertilizer (AGROVERT 6 13 46) | Nil | Nil | 230069400 | 5593b63b-e231-46c1-9ab5-b8e2fc9e7b21 | 2023-04-04 18:42 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 79
2023/04/03 | 18:34:15 | ADAD | Cocoa | Team 1 | Phase 3, Spraying of Cocoa plantation in the farm. | Spraying of Cocoa plantation in the farm, Phase 3 work | My spraying machine is not working fine | My spraying machine is not working fine | 230115207 | 96ecd3d8-9fac-4a75-9165-8d14ce929dc9 | 2023-04-05 03:28 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 80
2023/04/05 | 09:55:36 | DELU | Cocoa | Team 1 | Fumigation/Spraying on a cocoa farm using Insecticide and cocoa foliar | Fumigation/Spraying on a cocoa farm using Insecticide and cocoa foliar | Nill | In progress | 230234789 | eabffccd-7f16-4d94-b3e6-cf1fe2494f58 | 2023-04-05 13:40 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 81
2023/04/05 | 18:31:39 | OYOY | Vegetable | Team 2 | Irrigation of green house and open. Transplanting of tomatoes on the open field (platinum) | Continuation of transplanting of tomatoes | Late arrival of fuel | Nil | 230288371 | 081e0e8c-7b5d-41ef-9ed0-5dd6d0df3687 | 2023-04-05 17:33 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 82
2023/04/05 | 09:59:39 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Meeting up with the target | 230292682 | 4af4504a-3d2b-4687-9f6b-fdc8fc468231 | 2023-04-05 17:58 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 83
2023/04/05 | 09:57:08 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm, phase 3 | Spraying of Cocoa plantation in the farm, phase 3 Area | Nil | Work is moving | 230307080 | 8fca5ae5-2f94-4755-a58a-852794425ecb | 2023-04-05 19:37 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 84
2023/04/05 | 22:23:39 | JOTI | Vegetable | Team 1 | Drilling of holes for bamboo. Making of holes for transplanting. | Drilling of holes for bamboo. Making of holes for transplanting. | Nill. | Nill. | 230319776 | 3c2fe8f8-5816-481c-a20d-6672394ffa24 | 2023-04-05 21:25 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 85
2023/04/05 | 22:46:08 | EZAZ | Vegetable | Team 3 | Drilling of holes for staking of bamboos. making holes for transplanting. | Drilling of holes for staking of bamboos. making holes for transplanting. |  |  | 230321710 | b8c09f54-1236-4738-9c65-073811002cea | 2023-04-05 21:49 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 86
2023/04/06 | 17:35:39 | RODA | Cocoa | Team 1 | Spraying | Spraying | Nill | Good weather | 230505219 | 0fd14f49-6c68-48a5-902a-02c64abc45e8 | 2023-04-06 16:41 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 87
2023/04/06 | 21:31:38 | DELU | Cocoa | Team 1 | Fumigation/Spraying on cocoa farm using Cocoa foliar and insecticide | Fumigation/Spraying on cocoa farm using Cocoa foliar and insecticide | Nill | Progress | 230535867 | 9d26729a-875b-413c-b7ab-52b28f685f67 | 2023-04-06 20:32 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 88
2023/04/06 | 22:03:01 | JOTI | Vegetable | Team 1 | Drilling of bamboo holes. Making of holes for transplanting. | Drilling of bamboo holes. Making of holes for transplanting. | Nill. | Nill. | 230538874 | 617d8397-a684-45fb-a26c-e6e318747639 | 2023-04-06 21:04 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 89
2023/04/06 | 22:58:24 | OYOY | Vegetable | Team 2 | Transplanting of tomatoes and irrigation of green house and open field | Irrigation of green house | Nil | Nil | 230544289 | f2b2a22e-6743-4937-8139-9ab6c5fd595d | 2023-04-06 21:59 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 90
2023/04/06 | 22:49:15 | EZAZ | Vegetable | Team 3 | Drilling of holes for staking of bamboos and Making of holes for transplanting. | Drilling of holes for staking of bamboos and Making of holes for transplanting. |  | the drilling machine is draining my strength since am d only one drilling and it aches my body so much pls more hands/man power needed thanks. | 230694329 | 60eb8b3a-deac-4dc2-a43d-8e3458b79e97 | 2023-04-07 21:25 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 91
2023/04/07 | 22:20:06 | EZAZ | Vegetable | Team 3 | Drilling of holes for staking and staking of bamboos. | Drilling of holes for staking of bamboos . | Man power | milk needed please too much inhaling smoke from the drilling machine is disturbing | 230694331 | 9b6d7031-7577-4e02-9a7d-1a3dbe6dbc8b | 2023-04-07 21:25 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 92
2023/04/06 | 15:50:11 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm, Phase 3 Area | Spraying of Cocoa plantation in the farm, Phase 3 Area | Nil | Mine spraying machine is working fine now | 230783107 | a1bde5d3-5857-4441-abf1-7a638eeab839 | 2023-04-08 13:39 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 93
2023/04/07 | 21:18:41 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm, Phase 3 Area | Spraying of Cocoa plantation in the farm, Phase 3 Area | Nil | Work is moving | 230783125 | 63458f54-f159-48b8-b236-3b08bfd05655 | 2023-04-08 13:39 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 94
2023/04/08 | 14:37:08 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm, Phase 3 Area | Spraying of Cocoa plantation in the farm, Phase 3 Area. | Nil | Work is moving | 230783136 | 209df5b0-90ef-49e4-a440-4c541f20d73b | 2023-04-08 13:39 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 95
2023/04/08 | 21:10:48 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field | Irrigation of green house and open | Nil | Nil | 230823739 | 3f17d113-07b0-4882-9873-cdad15723479 | 2023-04-08 20:11 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 96
2023/04/08 | 22:14:02 | EZAZ | Vegetable | Team 3 | Staking of bamboos |  |  |  | 231016638 | 52c8d758-9c24-4592-9988-af1fd37212b2 | 2023-04-10 11:49 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 97
2023/04/10 | 20:57:34 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field | Irrigation of green house and open field | Generator issues | Nil | 231154546 | 5f34e69e-956f-4a1f-828e-d36d9b6a6911 | 2023-04-11 07:35 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 98
2023/04/11 | 15:39:50 | RODA | Cocoa | Team 1 | Spraying | Spraying | Good weather in the morning but there was rainfall in the evening | We experienced heavy rainfall when we supposed to go back in the afternoon | 231271249 | 9ac3221e-5a86-4866-8c24-86b41478b0ca | 2023-04-11 14:45 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 99
2023/04/11 | 19:33:10 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field | Irrigation of green house and open field | Late arrival of engineer | Nil | 231397405 | 9bea457b-4078-4b40-ad29-265db2880d3c | 2023-04-12 07:18 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 100
2023/04/12 | 19:37:04 | OYOY | Vegetable | Team 2 | Laying of drip line and irrigation of green house | Laying of drip line | Nil | Nil | 231581853 | 9befed1f-110f-4a37-aa7a-c6bbedd75452 | 2023-04-12 18:38 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 101
2023/04/11 | 12:56:42 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm, Phase 4 Area | Spraying of Cocoa plantation in the farm Phase 4 Area | Nil | Work is moving | 231721367 | ee23c760-f1c2-4ad5-af54-ca82c768e35a | 2023-04-13 11:41 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 102
2023/04/13 | 17:43:07 | RODA | Cocoa | Team 1 | Spraying | Spraying | Smooth weather | Was able to meet the target | 231799927 | d795eb92-b898-49a9-81c2-94c684460c8d | 2023-04-13 16:45 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 103
2023/04/13 | 23:18:16 | EZAZ | Vegetable | Team 3 | Placing of drip lines | placing of drip lines |  |  | 231848340 | 2ed6f9fb-70fa-4f6f-89af-4c9998873411 | 2023-04-13 22:20 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 104
2023/04/13 | 19:25:40 | OYOY | Vegetable | Team 2 | Irrigation of green house and open field | Irrigation of green house and open field | Late arrival of fuel | Nil | 231881913 | 41f7b788-c27a-4f0a-94d6-3ae88d23e088 | 2023-04-14 05:54 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 105
2023/04/13 | 12:39:43 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving on | 232050068 | ed8e5997-f8d0-4a2b-9118-e52340ea4a2f | 2023-04-14 20:34 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 106
2023/04/14 | 21:33:35 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 232050084 | 626112be-93f7-468b-8fcc-0b2e7dc31260 | 2023-04-14 20:35 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 107
2023/04/14 | 16:02:20 | OYOY | Vegetable | Team 2 | Laying of drip tape | Laying of drip tape | Nil | Nil | 232205708 | 86d9ea56-82cc-467f-b8e3-529dfa9f99d7 | 2023-04-15 19:45 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 108
2023/04/15 | 20:42:56 | OYOY | Vegetable | Team 2 | Laying of drip line | Laying of drip line | Nil | Nil | 232205712 | 1ed17c5a-84d7-47b4-a24d-c2eeeffc436a | 2023-04-15 19:45 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 109
2023/04/14 | 11:55:22 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Smooth weather | 232205989 | f4f8dbba-b302-4326-93cc-04e15500834b | 2023-04-15 19:49 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 110
2023/04/15 | 20:47:36 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 232205990 | ed24d906-31a2-40ef-a2fa-687a53d95f90 | 2023-04-15 19:49 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 111
2023/04/13 | 12:39:43 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving on | 232460790 | ed8e5997-f8d0-4a2b-9118-e52340ea4a2f | 2023-04-17 13:56 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 112
2023/04/13 | 10:16:37 | DELU | Cocoa | Team 1 | Fumigation/Spraying on cocoa farm using Cocoa foliar with insecticide | Fumigation/Spraying on cocoa farm using Cocoa foliar with insecticide | Nill | Good weather and availability of water use | 232461340 | e9fd7e3b-38e8-4b82-aa75-2285e8b30492 | 2023-04-17 13:59 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 113
2023/04/14 | 10:02:07 | DELU | Cocoa | Team 1 | Fumigation/spraying on a cocoa farm using fungicide | Fumigation/spraying on a cocoa farm using fungicide | Nill | Good weather | 232461342 | 2d4a3d8f-d340-4170-9bc0-ed82590050b7 | 2023-04-17 13:59 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 114
2023/04/15 | 08:24:02 | DELU | Cocoa | Team 1 | Fumigation/ Spraying on a cocoa farm using fungicide to avoid black pods |  | Nil | No delay | 232461345 | f846aa6e-888d-4cfb-accb-fa63773a38c6 | 2023-04-17 13:59 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 115
2023/04/17 | 14:57:14 | DELU | Cocoa | Team 1 | Fumigation/Spraying on a cocoa farm using fertilizer | Fumigation/Spraying on a cocoa farm using fertilizer | No delay | Progressing | 232461349 | 75f5a505-a995-4a3f-b44c-c40aa3b4795c | 2023-04-17 13:59 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 116
2023/04/17 | 15:22:43 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 232467300 | fa8d1d40-d780-4a15-8b44-d6265435c6d9 | 2023-04-17 14:26 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 117
2023/04/17 | 15:22:41 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 232467303 | 36112770-c35e-4cf8-9b01-16730a2d8f0e | 2023-04-17 14:26 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 118
2023/04/17 | 23:52:55 | JOTI | Vegetable | Team 1 | Laying of driplines on mulching films | Laying of driplines on mulching films | Nill. | Nill. | 232547135 | 3b83b9af-af4b-4a33-bb53-f06fa838ec68 | 2023-04-17 22:55 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 119
2023/04/17 | 14:54:00 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 232746575 | 3f610802-dc54-4f7f-bbab-bffbf7040af5 | 2023-04-18 16:50 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 120
2023/04/18 | 17:47:45 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 232746606 | e782e00e-f84a-4bfc-8ed3-2379762162c5 | 2023-04-18 16:50 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 121
2023/04/18 | 18:32:14 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 232757167 | 76ffc71b-e53e-481f-92f4-a5f1c5c40a7f | 2023-04-18 17:35 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 122
2023/04/18 | 23:23:26 | OYOY | Vegetable | Team 2 | Laying of drip tape | Laying of drip tape | Nil | Nil | 232790758 | 143bbd81-273e-4196-b029-57ed3fd76469 | 2023-04-18 22:24 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 123
2023/04/18 | 23:54:21 | JOTI | Vegetable | Team 1 | Cutting of mulching films for bamboo holes. Adjusting of mulching films. | Laying of driplines on mulching films. Adjusting of mulching films. | Nill. | Nill. | 232794387 | aaae38c2-0e1c-4643-9803-f318f752f6d7 | 2023-04-18 22:56 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 124
2023/04/19 | 19:47:36 | OYOY | Vegetable | Team 2 | Laying of drip tape | Laying of drip tape | Nil | Nil | 232989570 | 6ca600c9-438a-4654-9f3e-e21dc3b407c1 | 2023-04-19 18:48 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 125
2023/04/19 | 22:22:18 | JOTI | Vegetable | Team 1 | Laying of driplines on mulching films. Fixing of binding wire on bamboos. Covering of mulching films. | Laying of driplines on mulching films. Fixing of binding wire on bamboos. Covering of mulching films. | Starter got exhausted which is causing a big delay to the work progress, currently not available in the store also. | Nill. | 233010993 | 5cbe8eb9-f98d-4608-9844-a67043a20ee8 | 2023-04-19 21:26 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 126
2023/04/18 | 08:07:38 | DELU | Cocoa | Team 1 | Fumigation/Spraying on a cocoa farm | Fumigation/Spraying on a cocoa farm | Nill | No delay | 233334808 | f05cb159-4701-476b-87ce-9c7d92ac5a1d | 2023-04-21 15:10 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 127
2023/04/19 | 08:43:01 | DELU | Cocoa | Team 1 | Fumigation/ Spraying using fungicide on a cocoa farm | Fumigation/ Spraying using fungicide on a cocoa farm | Nill | In progress | 233334812 | a4edb36d-0eea-4fdf-9c5e-7f0cc296f767 | 2023-04-21 15:10 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 128
2023/04/20 | 09:31:11 | DELU | Cocoa | Team 1 | Fumigation/ Spraying using both fungicide and insecticide on a cocoa farm | Fumigation/ Spraying using both fungicide and insecticide on a cocoa farm | No water near by we have to go far distance to get it | The work is in progress | 233334818 | 2a3a78d8-7823-446b-9ca7-c390d7f0c298 | 2023-04-21 15:10 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 129
2023/04/21 | 16:07:16 | DELU | Cocoa | Team 1 | Fumigation/Spraying on a cocoa farm using foliar and insecticide | Fumigation/Spraying on a cocoa farm using foliar and insecticide | Nill | No delay, enough water to use | 233334825 | f0a04641-a156-4fe4-ac20-902ea8be4078 | 2023-04-21 15:10 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 130
2023/04/15 | 21:06:12 | EZAZ | Vegetable | Team 3 | Laying/Tensioning of drip lines. |  |  |  | 233380725 | fa09a47f-9a91-47f5-9607-3161c9a98095 | 2023-04-21 21:18 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 131
2023/04/17 | 20:12:18 | EZAZ | Vegetable | Team 3 | placing / Tensioning of drip lines | placing / Tensioning of drip lines |  |  | 233380728 | ebcc7636-34e6-4ab7-b5d7-d834dc72aef0 | 2023-04-21 21:18 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 132
2023/04/18 | 23:05:25 | EZAZ | Vegetable | Team 3 | Arranging of opened mulching films. placing / Tensioning of drip lines. | Arranging of opened mulching films. placing / Tensioning of drip lines |  |  | 233380735 | b8cabedd-498b-4a4d-8b7a-783fca8db9f4 | 2023-04-21 21:18 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 133
2023/04/20 | 23:46:00 | EZAZ | Vegetable | Team 3 | Drilling | Drilling and staking of bamboos |  |  | 233380741 | b38f7c21-23f4-4574-bf47-209065bef370 | 2023-04-21 21:18 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 134
2023/04/21 | 22:08:52 | EZAZ | Vegetable | Team 3 | Drilling and staking of bamboos. | Drilling and staking of bamboos |  |  | 233380746 | 266aa1e0-5a7a-4dd0-abfe-bccd068baa2d | 2023-04-21 21:18 |  |  | submitted_via_web | ezaz_mgl | vEyhG35agJ8ci5haXwXtix |  | 135
2023/04/22 | 08:44:20 | DELU | Cocoa | Team 1 | Fumigation/Spraying using both cocoa folia and cpyrus application on the cocoa farm | Work free | No delay | Good weather and availability of water supply | 233418543 | 33df861a-8c08-47ce-8a6b-6e3be9f83194 | 2023-04-22 07:47 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 136
2023/04/22 | 18:43:34 | OYOY | Vegetable | Team 2 | Drilling of holes and putting of bamboo |  | Nil | Nil | 233483051 | d1d0da64-c13e-4c9a-a8db-240abfa86b80 | 2023-04-22 17:45 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 137
2023/04/20 | 19:49:51 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 233489332 | 91bfd5b6-d52c-444a-93c6-cbf18e1745e8 | 2023-04-22 18:43 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 138
2023/04/21 | 20:14:29 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 233489337 | 2530797e-bea8-4b01-a5fc-412afa0cafe4 | 2023-04-22 18:43 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 139
2023/04/22 | 19:41:51 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 233489345 | ad442c7a-4d9c-4143-a92b-937298880a55 | 2023-04-22 18:43 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 140
2023/04/22 | 22:40:47 | JOTI | Vegetable | Team 1 | Drilling of bamboo holes. Fixing of bamboos on ridges. | Nill | Starter unavailable to begin laying of driplines causing delay to essential parts of the work. | Nill. | 233502290 | e0edf4e1-8a2f-4857-a154-50c7e71d0758 | 2023-04-22 21:43 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 141
2023/04/24 | 22:10:03 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 233959962 | fa3dc8b9-a0f8-4e05-a8ed-e6767760ae7b | 2023-04-25 18:31 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 142
2023/04/26 | 21:43:44 | OYOY | Vegetable | Team 2 | Laying of mulching film | Setting of drip tape and transplanting | Nil | Nil | 234502409 | dfa8a453-31fa-4337-a7a5-c3603777fe81 | 2023-04-28 05:29 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 143
2023/04/25 | 14:56:50 | DELU | Cocoa | Team 1 | Fumigation/Spraying of both insecticide and fungicide | Fumigation/Spraying of both insecticide and fungicide | Nill | No delay | 234770845 | 6fe50cee-863c-441e-88db-b65645885286 | 2023-04-29 09:12 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 144
2023/04/28 | 15:18:30 | DELU | Cocoa | Team 1 | Fumigation/Spraying using both fungicide and insecticide on cocoa farm | Fumigation/Spraying using both fungicide and insecticide on cocoa farm | No delay | Favorable weather | 234770851 | 701402c3-7568-493c-9b91-a6f80d42c594 | 2023-04-29 09:12 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 145
2023/04/29 | 10:11:11 | DELU | Cocoa | Team 1 | Fumigation/Spraying on cocoa farm using both the Insecticide and fungicide | Half Day | Nill | In progress | 234770853 | a19026a8-a5f8-4de7-9b47-be2c287b962b | 2023-04-29 09:12 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 146
2023/05/06 | 11:11:35 | OYOY | Vegetable | Team 2 | Laying of drip tape | Laying of drip tape | Nil | Nil | 236364643 | bac3d1a6-68dc-4ef0-b1f0-217be3479af8 | 2023-05-06 19:05 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 147
2023/05/02 | 23:11:40 | ADAD | Cocoa | Team 1 | Harvest of Cocoa plantation in the farm | Harvest of Cocoa plantation in the farm | Nil | Work is moving | 238710422 | 91605439-7db2-48a0-abc6-4ded0b46e990 | 2023-05-16 19:48 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 148
2023/05/03 | 19:16:39 | ADAD | Cocoa | Team 1 | Harvest of Cocoa plantation in the farm | Harvest of Cocoa plantation in the farm | Nil | Work is moving | 238710425 | f166f655-fc55-46a0-8ce6-a9dd1bc5c304 | 2023-05-16 19:48 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 149
2023/05/04 | 23:10:52 | ADAD | Cocoa | Team 1 | Harvest of Cocoa plantation in the farm | Harvest of Cocoa plantation in the farm | Nil | Work is moving | 238710427 | 8c345ddc-af43-4b03-a5f2-b73771134b78 | 2023-05-16 19:48 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 150
2023/05/16 | 20:45:36 | ADAD | Cocoa | Team 1 | Cleaning of weed in the cocoa plantation | Cleaning of weed in cocoa plantation | Nil | Work is moving | 238710429 | 8a7ca547-d4f9-4095-9929-052fa0b6023d | 2023-05-16 19:48 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 151
2023/04/27 | 19:54:29 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 238710441 | 4624fd16-32fb-4917-aee3-24fbda0b0ef7 | 2023-05-16 19:48 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 152
2023/05/01 | 11:37:04 | DELU | Cocoa | Team 1 | Fumigation /spraying on cocoa farm using both the Insecticide and fungicide | Fumigation /spraying on cocoa farm using both the Insecticide and fungicide | Nill | In progress | 239107952 | d1f43cf9-0765-4af3-85e1-8bd18eaad6e7 | 2023-05-18 09:06 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 153
2023/05/10 | 08:17:03 | DELU | Cocoa | Team 1 | Harvesting.. | Harvesting | Nill | No delay | 239108077 | e0a2fed2-a4f6-4372-bd17-2b65277e5df9 | 2023-05-18 09:06 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 154
2023/05/11 | 09:43:00 | DELU | Cocoa | Team 1 | Inspection on a new cocoa farm |  | Nill | In progress | 239108127 | 6440c293-3719-4de9-a651-8683d8351300 | 2023-05-18 09:07 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 155
2023/05/15 | 12:34:46 | DELU | Cocoa | Team 1 | Harvesting.... | Harvesting | Nill | Progress | 239108165 | 34220ab2-b7a5-4de9-b974-8dd989f38838 | 2023-05-18 09:07 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 156
2023/05/16 | 09:03:06 | DELU | Cocoa | Team 1 | Clearing on cocoa farm | Clearing on cocoa farm | Nill | Progress | 239108195 | 74a8abdc-bbd7-4a39-9987-2dbaf2c7b478 | 2023-05-18 09:07 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 157
2023/04/19 | 08:44:39 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 239482044 | 8d6a225f-a4a9-4a00-a2d1-728c9300ff94 | 2023-05-19 14:43 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 158
2023/05/19 | 13:02:48 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 239482050 | da3211b4-2ca5-476b-bd17-c03692c1c920 | 2023-05-19 14:43 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 159
2023/05/20 | 09:36:40 | RODA | Cocoa | Team 1 | Harvesting and breaking the Cocoa shell | Harvesting and breaking the Cocoa shell | NILL | Good weather | 239622618 | a71705f0-2b78-4082-8519-a1a95bb39c7e | 2023-05-20 08:39 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 160
2023/05/22 | 11:08:08 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 240009253 | 3ed8957a-0be1-4d2d-982b-0f0b3e7f59c7 | 2023-05-22 10:10 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 161
2023/05/04 | 07:55:59 | DELU | Cocoa | Team 1 | Harvesting the ripe and matured cocoa | Harvesting the ripe and matured cocoa | Nill | In progress | 240081707 | ca264b8b-d803-40e1-a8f3-cbff41b40fa8 | 2023-05-22 14:18 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 162
2023/05/18 | 16:28:05 | DELU | Cocoa | Team 1 | Pruning and harvesting | Pruning and harvesting | Nill | In progress | 240081712 | 6ac763c9-7a7e-4b1a-8c1f-0bb5c15dabe4 | 2023-05-22 14:18 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 163
2023/05/20 | 09:34:42 | DELU | Cocoa | Team 1 | Harvesting | Harvesting | Nill | In progress | 240081715 | 1ab3101e-7482-4fac-a845-6f223126952c | 2023-05-22 14:18 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 164
2023/05/22 | 10:26:40 | DELU | Cocoa | Team 1 | Fumigation/Spraying of insecticide and foliar on cocoa farm | Fumigation/Spraying of insecticide and foliar on cocoa farm | Nill | In progress | 240081716 | dfbb618e-e4c8-447f-864f-b949870800fc | 2023-05-22 14:18 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 165
2023/05/23 | 10:10:27 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 240264513 | 835b29ea-8754-42bd-96db-ae3f4d1643ed | 2023-05-23 09:12 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 166
2023/05/18 | 19:24:14 | ADAD | Cocoa | Team 1 | Harvest of Cocoa plantation in the farm | Harvest of Cocoa plantation in the farm | Nil | Work is moving | 240421003 | 6bd71da3-c225-4abb-86c0-bf292fbe8314 | 2023-05-23 18:09 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 167
2023/05/20 | 11:28:13 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spraying of Cocoa plantation in the farm | Nil | Work is moving | 240421030 | 655ef870-5b29-404a-a178-a55522ebce49 | 2023-05-23 18:09 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 168
2023/05/21 | 10:16:41 | ADAD | Cocoa | Team 1 | Spraying of Cocoa plantation in the farm | Spreading of Cocoa plantation in the farm | Nil | Work is moving | 240421035 | 379dd2d5-7ad3-406a-93d3-1e848538046f | 2023-05-23 18:09 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 169
2023/05/22 | 15:34:49 | ADAD | Cocoa | Team 1 | Spraying of insecticide (CYPRUS) in Cocoa plantation in the farm. | Spreading of insecticide (CYPRUS) in Cocoa plantation in the farm. | Nil | Work is moving | 240421040 | 3721a75b-6d18-4159-b8b6-9440c16cde3f | 2023-05-23 18:09 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 170
2023/05/17 | 15:27:50 | ADAD | Cocoa | Team 1 | Cleaning of Cocoa plantation in the farm | Cleaning of Cocoa plantation in the farm | Nil | Work is moving | 240421052 | 8a5fd6b4-234f-4127-99d1-63dd2a3ac180 | 2023-05-23 18:09 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 171
2023/05/24 | 15:06:47 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 240625320 | d88b10ff-2eb2-4d8a-9c0d-08e89d95a138 | 2023-05-24 14:08 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 172
2023/05/23 | 10:08:56 | DELU | Cocoa | Team 1 | Fumigation/Spraying using Insecticide Cyprus and foliar wacot bounty on cocoa farm | Fumigation/Spraying using Insecticide Cyprus and foliar wacot bounty on cocoa farm | Nill | In progress | 240633828 | 45fd3df9-f3fb-4d48-90d2-fa2910f7edfd | 2023-05-24 14:32 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 173
2023/05/24 | 15:31:15 | DELU | Cocoa | Team 1 | New cocoa farm discovery and prunning | Fumigation/Spraying using foliar and insecticide cpyrus | Nill | In progress | 240633839 | c837b2d9-e185-42a5-b8fa-69bfba6ed540 | 2023-05-24 14:32 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 174
2023/05/25 | 10:15:23 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 240828770 | f1aeb6ba-e64d-442d-9630-26c0c957407d | 2023-05-25 09:17 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 175
2023/05/25 | 15:44:05 | DELU | Cocoa | Team 1 | Fumigation/Spraying on cocoa farm using foliar and insecticide cpyrus | Fumigation/Spraying on cocoa farm using foliar and insecticide cpyrus | Nill | In progress | 240923310 | 2c55c724-105e-4067-92da-f94ad6141e95 | 2023-05-25 14:46 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 176
2023/05/26 | 10:28:47 | RODA | Cocoa | Team 1 | Spraying | Spraying | NILL | Good weather | 241123600 | 702c46b5-c92b-4886-b85d-4db1492faaae | 2023-05-26 09:30 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 177
2023/05/27 | 17:35:27 | ADAD | Cocoa | Team 1 | Spraying of insecticide CYPRUS in Cocoa plantation. | Spraying of Wacot Bounty on Cocoa to improve yield and quality of the pods during periods of poor growing conditions. | Nil | Work is moving | 241961384 | 31e1bf21-5171-4da5-9a9d-a850184e2d3c | 2023-05-29 19:24 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 178
2023/05/29 | 20:22:19 | ADAD | Cocoa | Team 1 | Spraying of CYPRUS is a non-systemic insecticide on a Cocoa plantation, in other to kill any pest that want to harm the plantation. Spraying of WACOT BOUNTY on Cocoa to improve yield and quality of the Pods during periods of poor growing conditions. | Spraying of CYPRUS is a non-systemic insecticide on a Cocoa plantation, in other to kill any pest that want to harm the plantation. Spraying of WACOT BOUNTY on Cocoa to improve yield and quality of the Pods during periods of poor growing conditions. | Nil | Work is moving | 241961388 | ca62645a-2551-409c-8cb0-36ed7cab34e6 | 2023-05-29 19:24 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 179
2023/05/24 | 15:37:59 | ADAD | Cocoa | Team 1 | Spraying of insecticide CYPRUS in the farm | Spraying of insecticide CYPRUS in the farm | Nil | Work is moving | 241961417 | 9b75cf8c-eebc-489f-846f-f955bf5ec801 | 2023-05-29 19:25 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 180
2023/05/23 | 19:09:19 | ADAD | Cocoa | Team 1 | Spraying of insecticide CYPRUS in Cocoa plantation | Spraying of insecticide CYPRUS in Cocoa plantation | Nil | Work is moving | 241961472 | 888e8696-874e-4923-b190-354ac8e65c8a | 2023-05-29 19:25 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 181
2023/05/26 | 09:41:52 | DELU | Cocoa | Team 1 | Fumigation/Spraying using foliar and Insecticide Cyprus on a cocoa farm | Fumigation/Spraying using foliar and Insecticide Cyprus on cocoa farm | Nill | In progress | 242166371 | 3d8ced5a-0aa3-4d33-93ca-dea04fa6b6bf | 2023-05-30 14:14 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 182
2023/05/30 | 15:10:55 | DELU | Cocoa | Team 1 | Fungicide using pumping method and herbicide on Cocoa farm | Fungicide using pumping method and herbicide on Cocoa farm | Nill | In progress | 242166388 | b5f51368-5f89-45f1-8de1-bf2b4b66ed31 | 2023-05-30 14:14 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 183
2023/05/30 | 16:21:06 | RODA | Cocoa | Team 1 | Clearing of grasses, application of fungicide and application of embicide | Clearing of grasses, application of fungicide and application of embicide | NILL | Good weather | 242199858 | c0b86429-cd70-41cc-9d84-b2fa8848d79a | 2023-05-30 15:24 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 184
2023/05/30 | 17:55:04 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. | Nil | Work is moving | 242276935 | 8d099481-3598-4fc7-aa44-e5d016e2f463 | 2023-05-30 18:40 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 185
2023/06/02 | 10:10:15 | RODA | Cocoa | Team 1 | Spraying of fungicide and embicide | Spraying of fungicide and embicide | NILL | Good weather | 242945091 | 6d549505-1bf4-4faa-9b97-91df2210b217 | 2023-06-02 09:12 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 186
2023/06/02 | 22:29:56 | JOTI | Vegetable | Team 1 | Staking of tomato plants on the new open field. | Staking of tomato plants on the new open field. | Nill. | Nill. | 243114814 | 7f19dbd6-2499-40eb-85b3-888b10fcc14d | 2023-06-02 22:09 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 187
2023/06/03 | 09:21:20 | RODA | Cocoa | Team 1 | Spraying fungicide and embicide | Spraying fungicide and embicide | NILL | Good weather | 243157436 | 3d00bb57-7b4c-4eec-9e49-281116e05e2f | 2023-06-03 08:23 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 188
2023/05/31 | 10:56:57 | DELU | Cocoa | Team 1 | Fumigation with mackie gold on cocoa pod using pumping method, spraying the weed with herbicide using paraeforce | Fumigation with mackie gold on cocoa pod using pumping method, spraying the weed with herbicide using paraeforce | Nill | In progress | 243597463 | d080abdd-5545-40f6-9509-68eba073c542 | 2023-06-05 14:34 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 189
2023/06/02 | 10:06:08 | DELU | Cocoa | Team 1 | Fumigation of fungicide using mackienie gold and spraying of herbicide using paraeforce | Fumigation of fungicide using mackienie gold and spraying of herbicide using paraeforce | Nill | In progress | 243597474 | bc48116d-f463-4d19-9388-e8e781ab719a | 2023-06-05 14:34 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 190
2023/06/05 | 11:36:55 | DELU | Cocoa | Team 1 | Harvesting | Harvesting | Nill | In progress | 243597485 | fd05df5b-8def-410f-b7de-5411d9f9fe6e | 2023-06-05 14:34 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 191
2023/06/01 | 14:46:28 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | We have delay of Water in the farm this morning also, we need to go to the river to get water today. | Work is moving | 243643242 | a88b6b09-d6ae-4123-a949-d9ecb4b8863c | 2023-06-05 17:04 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 192
2023/06/02 | 20:06:28 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Nil | Work is moving | 243643249 | 20c1004e-94d5-4960-96b7-c05343381502 | 2023-06-05 17:04 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 193
2023/06/03 | 18:29:50 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Nil | Work is moving | 243643376 | 71b7e5f1-259e-4b9c-956d-0a904d4a9249 | 2023-06-05 17:05 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 194
2023/06/05 | 18:03:15 | ADAD | Cocoa | Team 1 | Harvest of Cocoa in the farm | Harvest of Cocoa plantation in the farm | Nil | Work is moving | 243643382 | 4a4d4fb2-0f37-4656-80d7-b9cccd387e71 | 2023-06-05 17:05 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 195
2023/05/31 | 19:42:16 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. | Yes we have delay of Water in the farm, in the morning but it was resolved same morning. | Work is moving | 243643411 | c0910bee-0cb0-4415-bbaf-06ba2b691507 | 2023-06-05 17:05 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 196
2023/06/06 | 10:48:30 | RODA | Cocoa | Team 1 | Spraying of fungicide and embicide | Spraying of fungicide and embicide | NILL | Good weather | 243782765 | ba45d90e-c849-44a1-a70d-4e7869ce87b8 | 2023-06-06 09:51 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 197
2023/06/05 | 20:25:56 | JOTI | Vegetable | Team 1 | Staking of Tomatoes at New Open Field Section One, Phase Two | Staking of Tomatoes at New Open Field Section One, Phase Two | Nill. | Nill. | 243955983 | 5cba774b-907d-4174-969d-ff188a9c23f7 | 2023-06-06 20:03 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 198
2023/06/06 | 21:01:25 | JOTI | Vegetable | Team 1 | Staking of Tomato plants on new open field phase 1b | Staking of Tomato plants on new open field phase 1b | Nill. | Twine is finished | 243955984 | 19ccd383-2416-46b4-922a-b8c1f4a017da | 2023-06-06 20:03 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 199
2023/06/07 | 09:10:09 | RODA | Cocoa | Team 1 | Spraying of fungicide and embicide | Spraying of fungicide and embicide | NILL | Good weather | 244042546 | 0ba63b1f-9795-4cb8-b406-fb3796ca01e7 | 2023-06-07 08:12 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 200
2023/06/07 | 09:10:54 | DELU | Cocoa | Team 1 | Fungicide using mackienie gold and herbicide using paraeforce | Fungicide using mackienie gold and herbicide using paraeforce | Nill | In progress | 244441880 | 2bd75035-4378-4c58-889b-851139d4a9b9 | 2023-06-08 14:55 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 201
2023/06/08 | 15:52:51 | DELU | Cocoa | Team 1 | Fungicide and clearing using herbicide | Fungicide and clearing using herbicide | Nill | In progress | 244441884 | 9784740d-1abc-4264-b10f-6821e535583c | 2023-06-08 14:55 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 202
2023/06/08 | 23:24:21 | JOTI | Vegetable | Team 1 | Transplanting of Nurseries on open field. | Spraying of insecticide (Halakat) on open all tomatoes on open field. | Nill. | Nill. | 244541205 | 9f7e6bf1-487a-41f7-a057-2b5deb3d01ef | 2023-06-08 22:26 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 203
2023/06/09 | 10:15:09 | RODA | Cocoa | Team 1 | Spraying of fungicide and herbicide | Spraying of fungicide and herbicide | NILL | Good weather | 244617283 | af103b58-19c1-4455-ba3f-f80929d23ab2 | 2023-06-09 09:17 |  |  | submitted_via_web | roda1_mgl | vEyhG35agJ8ci5haXwXtix |  | 204
2023/06/09 | 17:23:59 | OYOY | Vegetable | Team 2 | Application of N:P:K | Spraying of TECNOKEL | Nil | Nil | 244742998 | a858e29e-bdc2-4ae6-b60b-4680ce4a8319 | 2023-06-09 17:39 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 205
2023/06/10 | 19:08:08 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Nil | Work is moving | 245334268 | b642870b-c58d-438e-87a8-7221be5dc3c2 | 2023-06-12 19:25 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 206
2023/06/12 | 19:36:23 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 245334280 | ee202f6a-5dd1-44db-8684-57897925b7f7 | 2023-06-12 19:26 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 207
2023/06/12 | 22:11:09 | OYOY | Vegetable | Team 2 | Erecting of bamboo and binding wire | Spraying of Insecticide( HALAKAT) CUCUMBER | Nil | Nil | 245348823 | aa0208ba-81c2-4987-bd40-dce610e7e0a2 | 2023-06-12 21:13 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 208
2023/06/12 | 23:54:18 | JOTI | Vegetable | Team 1 | Application of NPK fertilizer on Open Field phase 2a. | Staking of Tomato plants on open field phase 1b. | Insufficient workforce to complement the workload on ground. | Nill. | 245358693 | 1ac4e0ad-6df9-464f-b7c6-975b074bea14 | 2023-06-12 22:56 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 209
2023/06/13 | 22:11:44 | OYOY | Vegetable | Team 2 | Staking of cucumber | Spraying of Insecticide (ORIZON) on the cucumber | Nil | Nil | 245626162 | 4289e2a7-d926-4a8f-9597-cc5cbefe0023 | 2023-06-13 21:12 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 210
2023/06/13 | 23:42:07 | JOTI | Vegetable | Team 1 | Staking of Tomato plants on open field phase 1b. | Spraying of Technochel on tomato plants on open field around the Green Houses. | Insufficient workforce for workload. | Nill. | 245637137 | b6030a07-063f-440f-9e6c-8be9aa07b516 | 2023-06-13 22:45 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 211
2023/06/09 | 11:16:19 | DELU | Cocoa | Team 1 | Funmigation using mackenie gold and spraying of herbicide using paraeforce | Funmigation using mackenie gold and spraying of herbicide using paraeforce | Nill | In progress | 245799054 | 92d92a44-59fe-4587-9153-3171a92e801c | 2023-06-14 13:51 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 212
2023/06/12 | 11:10:56 | DELU | Cocoa | Team 1 | Funmigation with mackenie gold and herbicide with paraeforce | Funmigation with mackenie gold and herbicide with paraeforce | Nill | In progress | 245799068 | 1c7071a3-b788-448d-9d3b-81e8beef02aa | 2023-06-14 13:52 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 213
2023/06/13 | 11:41:30 | DELU | Cocoa | Team 1 | Harvesting | Harvesting | Nill | In progress | 245799079 | a35d17d3-927f-48ed-a484-3d1656d7f264 | 2023-06-14 13:52 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 214
2023/06/14 | 14:50:47 | DELU | Cocoa | Team 1 | Harvesting | Harvesting | Nill | In progress | 245799091 | c8fde0fa-e7b8-471d-a0e1-f0b6ccdd9388 | 2023-06-14 13:52 |  |  | submitted_via_web | delu_mgl | vEyhG35agJ8ci5haXwXtix |  | 215
2023/06/14 | 19:25:47 | OYOY | Vegetable | Team 2 | Staking of cucumber | Staking of cucumber, harvesting and spraying of Fungicide (SAFF) | Nil | Nil | 245884956 | c853a01f-afb0-4583-86bb-12d6c6c2801f | 2023-06-14 18:27 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 216
2023/06/14 | 23:27:18 | JOTI | Vegetable | Team 1 | Staking of Tomato plants on open field phase 1b. | Staking of Tomato plants on open field phase 1b. | More hands needed as the plants needs urgent staking. | Nill. | 245929623 | f84b9528-eabe-469d-8965-692077a59dd9 | 2023-06-14 22:29 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 217
2023/06/09 | 17:00:30 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Nil | Work is moving | 246158194 | 2491b25f-7562-43d3-833f-a105c5f575f3 | 2023-06-15 16:36 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 218
2023/06/13 | 17:17:01 | ADAD | Cocoa | Team 1 | Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 246158210 | 18203706-66f7-4ece-af0f-dcfa5ca79c51 | 2023-06-15 16:36 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 219
2023/06/14 | 23:04:50 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 246158226 | aee4ff04-c212-4131-a99e-f613d1d18618 | 2023-06-15 16:36 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 220
2023/06/15 | 17:29:50 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 246158236 | bcb9d1d1-4e5c-4dcc-9853-1c2175346997 | 2023-06-15 16:36 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 221
2023/06/15 | 23:41:36 | JOTI | Vegetable | Team 1 | Spraying of Halakat on open field phase 1&2 | Staking of Tomato plants on open field phase 1b. | Rainfall in the afternoon reduced the work obtained. | Nill. | 246237275 | 017fd12c-b01f-4ad8-8379-bf6861a40103 | 2023-06-15 22:46 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 222
2023/06/16 | 18:57:12 | OYOY | Vegetable | Team 2 | Spraying of Fungicide(SAFF) on 1a cocoa area | Spraying of TECNOKEL | Nil | Nil | 246459951 | ed43413e-61d0-4c59-9d80-281bca378416 | 2023-06-16 17:59 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 223
2023/06/19 | 23:23:53 | JOTI | Vegetable | Team 1 | Application of NPK fertilizer on Open Field phase 1b | Fixing of starters to lay flat (hose) for bed 2b. Laying of drip lines on beds 2b. | NPK fertilizer exhausted. Driplines exhausted. | More hands needed on site as work gets cumbersome on a daily basis. | 247126178 | 4a2b4fdd-b0e1-477f-8daf-b7494152717c | 2023-06-19 22:28 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 224
2023/06/17 | 17:33:13 | OYOY | Vegetable | Team 2 | Application of N P K to the tomato | Nil | Nil | Nil | 247475766 | f76163d1-ee4b-4939-8573-934a2f4c93d3 | 2023-06-21 07:31 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 225
2023/06/20 | 20:51:18 | OYOY | Vegetable | Team 2 | Staking of the tomato cocoa area | Spraying of Insecticide(HALAKAT) | Nil | Nil | 247475772 | dc2a1b20-91c3-455e-b237-8ed5db34443d | 2023-06-21 07:31 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 226
2023/06/16 | 21:16:30 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Nil | Work is moving | 247621842 | 9aabc31e-befb-49b6-aa04-988c81da73e5 | 2023-06-21 16:04 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 227
2023/06/17 | 19:55:19 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 247621856 | 3f6dfd0a-4a84-4fa3-95ff-e088422b6e2d | 2023-06-21 16:04 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 228
2023/06/19 | 19:59:22 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 247621873 | d60e0adb-b62f-4191-a494-3e2c4412d4e0 | 2023-06-21 16:04 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 229
2023/06/20 | 20:20:38 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 247621901 | d654d638-6dd3-48e4-ac76-24f8a59acb6f | 2023-06-21 16:04 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 230
2023/06/21 | 16:52:03 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 247621910 | 3da281dd-799b-4e63-9d98-b2885e0462e5 | 2023-06-21 16:04 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 231
2023/06/06 | 13:17:07 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of Paraeforce to kill the weed on the farm. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. | Nil | Work is moving | 247621952 | 050dbdd2-fadb-4e68-a38c-dd27eea241ae | 2023-06-21 16:04 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 232
2023/06/21 | 23:35:53 | JOTI | Vegetable | Team 1 | Staking of Tomato plants on open field phase 1b. Harvesting of Tomatoes on open field beside the greenhouses. | Harvesting of Habanero from greenhouse 5. | Rainfall delayed the spraying of red force agrochemical on open field. | Nill. | 247702497 | 46691e93-8d97-48d2-af57-50d0c22c7410 | 2023-06-21 22:41 |  |  | submitted_via_web | joti_mgl | vEyhG35agJ8ci5haXwXtix |  | 233
2023/06/22 | 17:51:06 | OYOY | Vegetable | Team 2 | Spraying of Red Force | Application of N P K | Nil | Nil | 248030168 | 4e664012-6baf-42ad-acea-8e8be6c9dcc5 | 2023-06-23 06:47 |  |  | submitted_via_web | oyoy_mgl | vEyhG35agJ8ci5haXwXtix |  | 234
2023/06/26 | 22:26:09 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 249002954 | 8884c526-826a-45cb-8b9a-a969b8a1634a | 2023-06-27 21:47 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 235
2023/06/27 | 22:43:29 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 249002958 | 0b25ee9b-5e22-42a8-b902-4a89502843bd | 2023-06-27 21:47 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 236
2023/06/24 | 16:27:10 | ADAD | Cocoa | Team 1 | Breaking of Cocoa pods and bring out the seeds for fermentation. | Breaking of Cocoa pods and bring out the seeds for fermentation. | Nil | Work is moving | 249003007 | e9ba9476-e10f-4e39-803f-83d258d70be2 | 2023-06-27 21:47 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 237
2023/06/23 | 21:42:00 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 249003051 | 36a5686a-952b-4574-9f6d-20fd72cb0ffe | 2023-06-27 21:48 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 238
2023/06/29 | 20:38:38 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 250075714 | 5825f959-606c-41e1-98f4-eca86f0fc0cd | 2023-07-03 21:08 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 239
2023/06/30 | 23:52:11 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | We have delay today because there is no water in the green House | Work is moving | 250075716 | 25ad9f5c-1ba4-44a7-a75f-224ddacd0f18 | 2023-07-03 21:08 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 240
2023/07/01 | 22:04:05 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 250075718 | a5eca251-9a2c-4a37-9c29-cafc7fea8926 | 2023-07-03 21:08 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 241
2023/07/03 | 22:06:51 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Nil | Work is moving | 250075720 | e6ddad4a-c11f-4afd-9c5a-5c1e087154ee | 2023-07-03 21:08 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 242
2023/06/28 | 23:58:53 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work | 250075731 | 461ae1bc-2c0d-4577-a8a2-695819fc59ac | 2023-07-03 21:08 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 243
2023/06/22 | 22:30:13 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 250075759 | 78468b3b-8629-4eaa-b82a-81bdeefe60c9 | 2023-07-03 21:09 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 244
2023/07/05 | 22:10:27 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 251055623 | 050805b4-11d5-45d2-9fa7-526d709076a7 | 2023-07-07 15:07 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 245
2023/07/06 | 21:45:03 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 251055630 | a33c0544-09c8-42a6-a718-f7209afd80f0 | 2023-07-07 15:07 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 246
2023/07/07 | 16:04:20 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Our bike that we use for transportation of Cocoa from farm to house need service. Work is moving | 251055634 | d7a28b0a-98c1-4505-974e-affb91bb8618 | 2023-07-07 15:07 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 247
2023/07/04 | 22:29:51 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 251055721 | 48455bf9-cd3d-4aaf-ab1a-b31f2604dda3 | 2023-07-07 15:07 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 248
2023/07/12 | 20:00:17 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 253687078 | 2ee2e2b2-8e9c-4000-9202-6f18fa05265e | 2023-07-18 10:38 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 249
2023/07/14 | 16:02:08 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 253687087 | af2cc3fe-492f-4c49-a4e1-f11b7e9b721f | 2023-07-18 10:38 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 250
2023/07/15 | 22:36:24 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 253687091 | dbdd5ee8-bfbd-4137-87d2-632da3a4c090 | 2023-07-18 10:38 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 251
2023/07/17 | 23:39:33 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Nil | Work is moving | 253687099 | 926d863a-bfe2-45af-bcd4-79acc5e19f89 | 2023-07-18 10:38 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 252
2023/07/11 | 23:56:17 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 253687130 | 07656168-9872-4001-af13-7cfbad47ec1f | 2023-07-18 10:39 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 253
2023/07/20 | 23:38:24 | ADAD | Cocoa | Team 1 | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Harvesting of Cocoa in the farm and breaking of the pods to bring the seed out for fermentation process. | Nil | Work is moving | 255885914 | 0d34afb8-b43c-4aae-92ed-dbb8c3947729 | 2023-07-26 20:27 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 254
2023/07/21 | 21:46:11 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Nil | Work is moving | 255886004 | 40700c6f-b94f-4459-b87f-97deecd80c75 | 2023-07-26 20:28 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 255
2023/07/24 | 17:27:10 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Nil | Work is moving | 255886007 | 5eb673a0-8f06-46f6-9b7d-1155e20adfe2 | 2023-07-26 20:28 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 256
2023/07/25 | 18:36:01 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Nil | Work is moving | 255886009 | 3edbb96a-5e5a-48a9-896b-bc258f26276c | 2023-07-26 20:28 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 257
2023/07/26 | 21:25:29 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Nil | Work is moving | 255886012 | 84cf4966-bf69-48b5-9649-023d22f8b04d | 2023-07-26 20:28 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 258
2023/07/19 | 21:17:54 | ADAD | Cocoa | Team 1 | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Spraying of MACKECKNIE GOLD on Cocoa Pods, for the period of maturation of the pods it is recommended to change over to a contact fungicide. Spraying of SUPER GRO in the farm is to enhances the benefits of plant foods and fertilizers. Harvest of Cocoa and breaking for fermentation process. | Nil | Work is moving | 255886025 | e1f1e5cb-3a28-4759-934a-874aba9b5592 | 2023-07-26 20:28 |  |  | submitted_via_web | adad_mgl | vEyhG35agJ8ci5haXwXtix |  | 259